## Summary (hidden)
|  | CareTrekker |  | Summary
| Client | Domain | Technology | Total Hours | 382.4
| CareTrekker | Health Care |  | Total Person Days | 47.8
|  |  |  | Total Person Months | 2.39
| Similar Projects Done | Domain | Technology | Person Hour Rate
|  |  |  | Total Cost | Person hour rate is not set
Date
Prepared by
Reviewed by
Approved by
Collaterals/Artifacts provided by the customer
1
Technical Risks
1
2
3
4
5
Functional Risks
1
2
3
4
5
Assumptions and Dependencies
1
2
3
4
5
6
7
8
Third Party Tools/products/components to be used
1
2
3
Reusable components considered
1
2
3
Reusable components to be created
1
2
3
* | PLEASE FILL IN THE NECESSARY DETAILS BY EXPANDING THE SECTIONS ABOVE. ANY THIRD PARTY TOOLS, RE-USABLE COMPONENTS USED SHOULD BE MENTIONED HERE
* | SECTION ON THE RIGHT - PREPARED BY, REVIEWED BY AND APPROVED BY HAS TO BE FILLED IN WITH DATES
* | ASSUMPTIONS AND DEPENDENCIES TO BE CARRIED INTO THE PROPOSAL / WO SHOULD BE MENTIONED HERE

## Resource Loading
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | Total | Rate | Cost
System Understanding
Python Library
EDT Test App
Testing and rework
UAT
Warranty
Project Management | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [32 empty] | 20 | 30 | 600
Application Developer | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | [32 empty] | 360 | 28 | 10080
Tester | [5 empty] | 40 | 40 | 20 | 20 | 10 | [32 empty] | 130 | 24 | 3120
Total | 42 | 42 | 42 | 42 | 42 | 82 | 82 | 62 | 42 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510 |  | 13800
Contingency @10% | [44 empty] | 15180

## Estimation-Summary
# | Factors and Items considered | Estimated Hours | Buffered Estimate | Budgeted Y or N? | Method Used | EFFORT DISTRIBUTION PERCENTAGES
A | Estimated Direct Effort
1 | Project Management | 16 | 16 | Y | Percentage | Project Management | 5% | 8%
2 | System Study | 40 | 40 | Y | Percentage | Requirements | 12.5% | 8%
3 | Application Design | 16 | 16 | Y | Percentage | Design | 5% | 6%
4 | Development | 160 | 160 | Y | Percentage | CUT | 50% | 50%
5 | QA Testing | 144 | 144 | Y | Percentage | QA-Testing | 45% | 20%
6 | SQA | 0 | 0 | N | Percentage | SQA | 0% | 2%
7 | Program Management | 0 | 0 | N | Percentage | Program Management | 0% | 2%
8 | Review | 3.2 | 3.2 | Y | Percentage | Review | 1% | 2%
9 | Rework | 3.2 | 3.2 | Y | Percentage | Rework | 1% | 2%
10 | Installation | 0 | 8 | Y | Days | Installation | 1
11 | Documentation Development | 0 | 0 | Y | Days | Doc Dev | 0
12 | Client Training | 0 | 0 | Y | Days | Client Training | 0
13 | End User Training | 0 | 0 | Y | Days | End-User Training | 0
B | Post Implementation Effort |  |  |  |  | Post Implementation Effort
1 | Warranty | 0 | 120 | Y | Days | Warranty | 15
2 | UAT | 0 | 80 | Y | Days | UAT | 10
C | Total Estimated Final Effort (C=A+B) | 382.4 | 590.4
| Buffer % |  | 0% | Budgeted Effort |  | 590.4
| Customer Version | Estimated Hours | Buffered Estimate
| Development | 222.4 | 430.4
| Testing | 144 | 144
| Project Management | 16 | 16
Note on G4: Project Monitoring, PM Reviews, PPR etc.,
Note on G5: Study of existing system, Requirements discussion, KT, Analysis
Note on G6: Software Design, Architecture, R&D, POC, HLD, LLD docs
Note on G7: Coding, Unit Testing
Note on G8: nSure Testing - Internal
Note on G9: No. of Hrs. in a day x No. of days x No. of resources
Note on G11: Review of all the work products of the project
Note on G12: Rework Effort for all the project work products
Note on G13: Deployment, Verification No. of Hrs. in a day x No. of days x No. of resources
Note on G14: Help manuals, User Guides etc No. of Hrs. in a day x No. of days x No. of resources
Note on G15: Client project staff training No. of Hrs. in a day x No. of days x No. of resources
Note on G16: Client end-user training No. of Hrs. in a day x No. of days x No. of resources
Note on G18: Usually (number of days x hours)
Note on G19: No. of days for Post delivery UAT support Usually (number of days x hours)

## Estimation-Detail
S.No | Functionality | Final Effort | Development and integration effort | Webservice integration effort | Other effort | Description | Overview | Remarks
Modules
1 | System Understanding
| Get Input / Output of the Current System. Understand current process. | 0 |  |  |  | 40 hours added to summary
| Get Certification information from the client | 0
| With Certification information, and WSDL test SOAP Request and verify SOAP Response. Use SOAP UI for this. Test all 7 methods. Get Sample data from client or read API documents | 0
2 | Implementation
| Develop Python library (EDT). | 80 | 80 |  |  | Library should have implementation for below methods > Upload > Submit > Download > List > Info > Delete > Update > typ_list
| Develop EDT Test App | 80 | 80 |  |  | Will use EDT library to send test data.
3 | Confirmance Testing |  |  |  |  | Tester will do this using EDT Test APP
| Test using EDT Test App - added to summary |  |  |  |  | Test 90+ Test Cases using EDT Test App - added to the summary
4 | Others (NFR, Software setup etc.)
| Deployment/Library Installation/Software Setup / Logging / Audit | 0 |  |  |  | Added to summary under installation

## Person Hour (hidden)
PLEASE SELECT THE NECESSARY CODE APPLICABLE TO YOUR TYPE OF PROJECT
ITEM | CODE | MANHOURS | .NET
Very Simple Form | VSF | 4
Simple Form | SF | 8
Average Form | AF | 16
Complex Form | CF | 24
Very Complex Form | VCF | 40
Very Simple Task | VST | 8
Simple Task | ST | 16
Average Task | AT | 36
Complex Task | CT | 40
Very Complex Task | VCT | 60
Simple Report | SR | 8
Average Report | AR | 16
Complex Report | CR | 24
Very Complex Report | VCR | 36
Simple Form | VBSF | 16 | VB .NET
Average Form | VBAF | 24
Complex Form | VBCF | 40
Simple Report | VBSR | 16
Average Report | VBAR | 24
Complex Report | VBCR | 32
Simple DB Object | VBSD | 2
Average DB Object | VBAD | 9
Complex DB Object | VBCD | 20
Simple Control | VBSC | 45
Average Control | VBAC | 65
Complex Control | VBCC | 76
Simple Form | OSSF | 20 | OSG
Average Form | OSAF | 36
Complex Form | OSCF | 48
Very Complex Form | OSVCF | 104
Simple Report | OSSR | 20
Average Report | OSAR | 36
Complex Report | OSCR | 48
Very Complex Report | OSVCR | 104
Simple DB Object | OSSD | 8
Average DB Object | OSAD | 16
Complex DB Object | OSCD | 24
Simple Control | OSSC | 36
Average Control | OSAC | 56
Complex Control | OSCC | 80
Very Complex Control | OSVCC | 104
Simple re-usability factor | OSSRF | 8
Average re-usability factor | OSARF | 16
Complex re-usability factor | OSCRF | 24
Simple design factor | OSSDF | 32
Average design factor | OSADF | 48
Complex design factor | OSCDF | 56
Simple Integration | OSSI | 32
Average integration | OSAI | 56
Complex integration | OSCI | 80

## Reference (hidden)
WBS | Meeting
FP | Discussion
Use Case | MOM
Percentage | Metrics
Days
Other

## Data (hidden)
Confidence Factor
61-70 | 2
71-80 | 1.75
81-90 | 1.5
91-100 | 1.25
Priority Factor
1 | 1 | Very High
2 | 0.9 | High
3 | 0.8 | Medium
4 | 0.7 | Low
5 | 0.6 | Very Low